RETENTION THREE-YEAR PLAN

During the Fall of 2007 and the Spring of 2008 a Retention Proposal was developed which outlined problem statements in regards to retention issues at FHSU.  Possible solutions to these problems were also discussed in the proposal.  The proposal was based on the following statement from the Dare to Dream Initiative.

Establish proposals to increase student retention and graduation at FHSU.  These proposals address the need to bolster our institutional retention as outlined in Dare to Dream Design Element 1, Number 5; “Improve student retention on the Hays campus, thereby producing 250 more registered students.”

In the Spring of 2009, Dr. Tisa Mason, Vice-President of Student Affairs, charged the retention committee to examine the problem statements from the original proposal and present ideas to begin to implement the solutions.  Task force teams were appointed to look at seven areas where FHSU could work to improve retention.  Four areas examined strategies for specific student populations.  These areas included:

- retention of students undecided about their major

- retention of students of color

- retention of students living off campus

- retention of students with an ACT score of under 16

The other three areas examined specific strategies for the retention of all students.  These included the following:

- implementing new and coordinating existing early warning systems

- improving and expanding the First Year Experience Program

- creating a Parent’s Program

The teams were given the charge of providing strategies that could be implemented to improve retention and graduation rates at FHSU over a three year period.  The results of each task force are outlined below.

Task force committees will continue to meet to ensure follow through and assessment on strategies implemented.  Chairpersons of each task force are expected to enlist the assistance of other campus entities for input as needed, and are encouraged to add people to their committees as necessary.

RETENTION OF UNDECIDED STUDENTS

2009-2010

- Review past five years of FHSU Student Survey of Advising for Undecided Students

- Review past five years of Career Counseling Survey

- Review feedback from 08-09 Career Planning and Development Class

- Research alternative terminology for undecided classification

- Answer the questions:  Are we meeting the advising and career goals for undecided students?

- Advisor meeting requirements determined by admit status

- Refine communication plan by identifying key responsibilities and process that need to be addressed (e.g. finalizing enrollment, course materials, orientation, drop/add)

- Collaboration with student services and academic departments (e.g. workshops for students and academic advisors, majors fair, academic department visits)

- Promote usage of What-If Scenarios in TigerTrack Online Services

- Create linkage to CSI for undecided students

- Create tracking program for new undecided students

2010-2011

- Review retention data from F09 freshmen

- Educate undecided students on taking IDS 100 Career Planning and Development and individualized career counseling appointments (this is not a goal for first-semester freshmen)

- Expand TIGER Series for Faculty and Staff in working with career selection

- Provide education planning through exploration of degree summaries for undecided sophomores

- Encourage major selection by completion of 45 hours of general education course work

- Review tracking to determine reason undecided students

- Evaluate communication plan and other programs provided

- Explore model and options for peer advisors

- Implementation of alternative terminology for undecided

2011-2012

- Review retention data from F09 and F10 freshmen

- Track former undecided students who have declared a major

- Evaluate communication plan and other programs provided

- Implement peer advisor model at FHSU

- Initiate or modify programs based on continuous quality improvement model

RETENTION OF STUDENTS OF COLOR

The Students of Color Retention Task Force was established to improve the retention rates of FHSU students of color who are taking classes on campus. The task force has been charged with becoming knowledgeable how students of color who take classes on campus experience FHSU and to design strategies to increase retention and graduation rates for this population. A significant issue impacting the success of students of color attending a predominantly white campus is the importance of recruiting a critical mass (defined as a minimum of 5%) of like students. Therefore, this task force will also examine recruitment strategies. To accomplish our charge we will become knowledge about the FHSU student of color on-campus experience by examining data and engaging in qualitative research. We will study best practices at other institutions. We will use our knowledge and evidenced-based decision making to design retention and recruitment strategies, evaluate programs, and assess effectiveness.

To begin our work, initial plans include the following strategies:

2009-2010

- Study the existing demographic and descriptive data to document status of students of color on FHSU campus to include:

  - Academic profile

  - Retention rates

  - Graduation rates

  - Residency status

  - Academic program distribution

  - NSSE data

  - Education Dynamics Data

  - Advising Satisfaction Data

- Identify data needs regarding students of color co-curricular involvement and design systems to collect/extract that data

- Conduct focus groups with high achieving students of color regarding recruitment practices, student engagement, and academic satisfaction

- Create an inventory of what is working well regarding the recruitment and retention of students of color

- Identify best practices for recruitment of students of color at other institutions and design FHSU strategies in consultation with the Admissions Office

- Evaluate the quantity and effectiveness of current culturally-based student activities

- Evaluate and develop/enhance departmental mentor programs

  - Faculty to student

  - Student to student

- Work jointly with the Early Warning Systems Task Force to identify funding sources/grants for a summer bridge program; apply for grant

- Review this document and update as appropriate

2010-2011

- Continue to collect and study data

- Implement summer bridge program if funded

- Create strong linkages between students of color programs and undergraduate research

- Implement and evaluate new recruitment strategies based on prior year research

- Identify funding sources/grants to begin a McNair Program

- Design strategies to specifically strengthen the following NSSE items:

  - Had serious conversations with students of a different race or ethnicity than your own

  - Had serious conversations with students who are different from you in terms of their religious beliefs, political opinions, or personal values

- Work with academic affairs and student affairs to create faculty and staff development opportunities regarding learning and retention of students of color

- Assess the level of an existing career focus among students of color; the evaluate use of career exploration and career services among students of color; design strategies as appropriate

- Explore service learning opportunities/actives for students of color – with a particular focus on how those activities are, or can be, tied back to home communities

- Review this document and update as appropriate

2011-2012

- Implement any new initiatives regarding strengthening the career focus for students of color

- Implement McNair Program if funded

- Study how many students of color are participating in study abroad programs as well as barriers and opportunities related study abroad experiences; design strategies as appropriate

- Review this document and update as appropriate

RETENTION OF FIRST YEAR STUDENTS LIVING OFF CAMPUS

2009-2010

- Parent information regarding living off campus as opposed to living on campus. (INTEGRATE INTO PARENTS PROGRAM, a session for off campus living is already included in this years parent orientation)

  - Make sure parents get information regarding services even though students live off campus

  - Make sure parents have access to campus events to remind students

- At orientation as all students where they are going to live during the year

  - e.g.,  Everyone living in McMindes stand, then everyone living in Wiest stand, and then everyone living off campus with their family stand.  This would let people look around and see who else is living off campus

- Create a T.I.G.E.R.S. Series workshop about living off campus and getting engaged

2010-2011

- Special group (with advisor/mentor) for students living off campus. (POSSIBLY A FEW O.A.’S AS MENTORS)

  - Help them get/stay involved on campus

  - Give them a sense of belonging/sense of family

  - Facebook page and/or TigerConnect Group for students living off campus.

  - Notify them of and invite them to events

  - Opportunity to socialize with other off campus students

2011-2012

- FYRE Program for off campus students

RETENTION OF AT-RISK STUDENTS BELOW 16 ACT

The purpose of this program is to provide a network of comprehensive university programs and services that assists our students in enhancing their academic potential.  Through collaborative partnerships within the university community, each student is afforded the opportunity to succeed.

Criteria for Program Participation

All incoming on-campus first-time freshmen are required to participate in this program if the student does not meet the Kansas Board of Regents Qualified Admission Requirements and has an ACT Composite lower than 16.

Program Elements

- MAXIMUM OF 12 credit hours –

- Students will be advised in AACE and be undecided-degree seeking students (000-0000C)

- Succeeding in College Course (IDS 103)

- 9 hours of General Education Foundational Courses (first semester)

- 9 hours of General Education and 3 hours of desired major or additional General Education course (second semester)

- Out of state students must complete 24 hours with a 2.0 GPA in 12 months.  All courses must be at FHSU

- Tiger Connection Meetings

- Tiger Connection Appointment 1 (resource connection based on admission information prior to 10th day of classes)

  - Tiger Connection Appointment 2 (class progress between 11th - 20th day of classes)

  - Mid-term Appointment

  - Pre-enrollment Appointment

  - End of semester Appointment

- Academic Advising and Coaching

- T.I.G.E.R. Series Workshop

Assessment Criteria

- Retention from semester to semester

- Successful academic progress

- Utilization of referral resources

- Post program assessment – student view of what worked and what didn’t

EARLY WARNING STRATEGIES

2009-2010

- Use Education Dynamics to help identify students who may need extra assistance or be "at risk".

- Identify FY minority students (Hispanic, African American, students with disabilities, etc.) and coordinate with Diversity Affairs on ways to integrate and support these students as they transition to the university.  Establish a mentor program.

- Target and follow up (emails, mailings, phone calls) with all students who have been admitted in the window, or have a certain ACT score.

- Follow up with students who receive a "not attending letter" from the Student Affairs Office.  This follow up could be by phone or email.  Possibly contact Advisor and involve them.   Would need to identify who should make the follow up, GA, Asst. VP, Faculty Associate, etc.

2010-2011

- Utilize the established Faculty Associate and FYRE program in the Res. Halls. This program could be valuable resource in connecting with "at risk" or students in academic trouble they are assigned to.  Possibly a Faculty Associate Advisory Board could be established that would assist with training of Faculty Associates, maybe even FYRE Associates; assess and evaluate program based on learning outcomes.

- Request a list of all 1st semester full time VC students, encourage them to sign up and utilize SmartThinking.  Follow up around midterm with students to encourage them to be in contact with their teachers to see what their grades are at mid-term and if they are "in trouble" provide information on services that can help them, or if they should consider dropping the course.

2011-2012

- Consider putting together a FYE group for first year students who live off-campus, with a student mentor and Faculty Associate.  Would need to look at how to compensate these positions.

FIRST YEAR EXPERIENCE

2009-2010

- Revamp Tiger Pre-Enrollment to better incorporate transitions information

- Tiger Connect (Education Dynamics)

  - Present information to students at Tiger Pre-Enrollment regarding Tiger Connect

  - Investigate FHSU 101 or Tiger Connection class with an online curriculum similar to freshman seminar

  - Work with Early Warning System group (& Multi-Disciplinary Threat Assessment Team) to use Tiger Connect data

  - Use Tiger Connect data for assessment—number of people responding to the survey questions; number of freshmen retained to sophomore vs. those who didn’t use the program, etc.

- Hire an FYE student coordinator to work with Tiger Connect and the Augustfest brochure

- Assess and alter Freshman Orientation, building on last  year’s successes

  - Increase size of Tiger Transfer Orientation by not limiting capacity

  - Reassess Student of Color and International Student Orientations

- Better incorporate the TIGERS series into FYE

  - Investigate the possibility of videotaping and putting the series on the web for a virtual connection & use with parent program

    - Put a counter on the site to assess hits

- Grow FYRE program into Wiest Hall

2010-2011

- Assess FYE learning outcomes

- Leadership Live & Learn Community, under the direction of Jill Arnsdorf and Tisa Mason

- Work with Parent Association group (may be able to utilize Tiger Connect)

- Assess and redevelop FYRE program in Residential Life with strategic benchmarks, learning outcomes, and assessment.

  - Assessment:  need objectives and regular FA / SAM meetings

  - Create a standardized process for midterm discussions, finals, etc.

  - Need a standardized assessment of FA effectiveness

  - Utilize hall grade reports

  - Increase FYRE programming in the halls with mentors for undecided students

- Better market FYE

  - Create an FYE logo and theme

  - Create a webpage with a common theme

  - Build calendars with events of particular interest to freshmen

2011-2012

- Develop an off-campus FYRE program

- Continue to assess the program and search for best practices / potential initiatives

  - Investigate the possibility of hiring an FYE grad or coordinator to better coordinate the framework of the program.

- Investigate ways to involve the FHSU Honors Society with freshmen as mentors

FAMILY ENGAGEMENT

The Parent Engagement Task Force was established to enhance and support a closer relationship between the University and family members; to support the recognition of student achievement and enhance the quality of student life; to identify and cultivate support for the University; and to maximize the potential of family involvement in achieving University goals. To accomplish our charge we will become knowledge about FHSU parent and family relations programs and services currently in existence at FHSU. We will assess the needs and interests of our students and their families and study best practices at other institutions. We will use our knowledge and evidenced-based decision making to fulfill our purpose.

To begin our work, initial plans include the following strategies:

Strategies for 09-10

- Determine mission and goals of the program

- Identify and parent and family programs, services, and resources currently in existence at FHSU

- Gather feedback from families on what we already offer

- Answer the question:  What does a family-friendly institution look like?

- Identify linkages between family programs and retention

- Create family support programs for student surprises (e.g. Send your student a smile, birthday packages)

- Create a Legacy pinning ceremony

- Increase “tigerizing” of families at campus events

Strategies for 10-11

- Revise parent/family orientation (at Pre-enrollment & Move-In

  - Provide Spanish Translation for key sessions

  - Begin collecting names of parents/families

- Build / improve electronic communications with families

  - Update / improve website

  - Study best practices regarding IM, E-mail, and Parent listservs

  - Partner w/ UR on Newsletter, e-news

- Move Family Day to Spring

- Create a mechanism to inform families of ongoing campus  events & issues

  - Involvement invitations

  - Update information/family alerts (ex:  fire alarms)

- Create a Parent/Family Association

- Create Parent/Family presence at SRPs

- Create family pulse surveys (University of Michigan)

Strategies for 11-12

- Implement Family Association

- Create Family Network Group (with year 1 mentors?)

- Begin Monthly Dial-in Chats (web or phone) with Parents

- Create On-site “Coffee on Campus” Program for Families

- Evaluate effectiveness of programs established in 10-11

- Begin studying best practices regarding Parent fund raising