DRAFT

Student Spotlight Video Procedure

Our committee has met on a couple of occasions and we have a draft procedure with regard to the student spotlight videos to be produced and used on the FHSU web site.  We met with informatics and Steven is very flexible and willing to provide assistance to us.

Please feel free to give us any feedback regarding this procedure.  I have produced a form that would be submitted online and that form can be found at

Procedure:

- FHSU faculty/staff fill out student spotlight video form online.

- Form will be submitted to Jon Armstrong for review, which begins approval process.

- Forms will be sent to SAT every Thursday for approval.

- SAT will send feedback of approval/disapproval back to the student spotlight video committee.

- Once approved, the committee will contact student to schedule time and date for production.

- Informatics will email video to committee for final review.

- Committee will communicate with Andy Tincknell to load video to the FHSU YouTube site.

- Committee will notify department that video is complete.

- Department can access YouTube site in order to load to their respective web site.

- Student Spotlight Video committee will keep all submitted forms.

Goals:

- Provide an opportunity for all Student Affairs staff an opportunity to be involved in promoting FHSU.

- Produce six student spotlight videos by December 21st launch date.

- Produce twelve videos by March 1st, 2010.