## SNU F26
Fort Hays State University
Cross-Border (SNU) Timeline Fall 2026
All Dates and Times are U.S. Central Time-zone
(8/31/26-12/18/26 - 16 weeks)
BOOKMARK THE TIMELINE - DO NOT DOWNLOAD AS DATES ARE SUBJECT TO CHANGE - Updated 7/20/2026
Action Item |  | SNU | Who
Pre-term |  |  | Lead | Support | Aware
Deadline for chairs to have FHSU Online Course Requests submitted to the Registrar |  | 2026-07-27 | GA | Chairs | Partner
Language proficiency status report (4 weeks prior) |  | 2026-08-03 | Students | HLI | IA
Faculty Professional Development - New/Returning |  | 5-7 Aug | GA | Chairs
Registration Templates |  | 2026-08-10 | GA | REG | Partner
Teaching Assignments entered and cross-checked in Workday for fall 2026 |  |  | Chairs | Registrar | BB
FHSU Faculty Appointment Forms - New Hires |  | 2026-08-10 | HR |  | Faculty
FHSU Faculty Appointment Forms – Returning |  | 2025-08-10 | HR |  | Faculty
Admission and Transcript reports: Late Admits Deadline (3 weeks prior) |  | 2026-08-10 | Partner | IA | REG
Final day to Submit Language proficiency score (2 weeks prior) |  | 2026-08-17 | IA |  | Partner
Registration Batch Load Roster (Wednesday) |  | 2026-08-24 | Partner | REG | GA
Register Students (Pre-check-Workday registration-Blackboard load*) (Friday) |  | 2026-08-26 | GA |  | Registrar - TS
Faculty arrive on campus |  |  | Faculty |  | Partner
Week 1 |  | August 31 - September 4
Classes Begin (Monday) |  | 2026-08-31 | Faculty |  | Students
Registration Batch Load Roster (first roster update by Monday) |  |  | Partner | REG | GA
Registration at partner school |  |  | Partner
Roster Discrepancy Check (Workday/Blackboard) (ongoing through September 11) |  |  | Faculty | GA/REG
Full refund period for students to drop courses (ongoing through September 11) |  |  | Partner |  | SFS
Registration Batch Load Roster (second roster update by Thursday) |  |  | Partner | REG
Week 2 |  | September 7- September 11
Registration Batch Load Roster (final update by Thursday) |  |  | Partner | REG | Partner
ASC and CbyD - list of courses and faculty with contact information (Thursday) |  |  | Partner | GA | IC
Full refund period ends for students to drop courses |  | 2026-09-11 |  |  | Students
Week 3 |  | September 14 - September 18
Enrollment Projections for Spring 2027 Provided to FHSU |  |  |  |  | Partner
Application for Completion (Intent to Graduate) for F26 sent to REG |  |  | Partner | REG
Mid-Autumn Festival break - (Make-up days - yet to be determined)
Week 4 |  | September 21 - September 25
Inform faculty if the student dropped/withdrew after 4 weeks |  |  | GA |  | Faculty
SFS begins invoicing process |  |  |  | SFS | Partner
Week 5 |  | September 28 - October 2
Tentative Holiday Break - (Make-up days Oct. 11)
Spring 2027 Projections Finalized |  |  | Chairs | GA | Partner
Week 6 |  | October 5 - October 9
Final Invoice Processed - Wiring of Payment Begins |  |  | Partner |  | SFS
Textbook List (reviewed and confirmed for Spring 2027) |  |  | GA | Chairs | Partner
Week 7 |  | October 12 - October 16
ASC/CbyD Review by Academic Department |  |  | Chairs |  | Partner/REG
Week 8 |  | October 19 - October 23
Teaching Assignments for Spring 2027- initial |  |  | GA | Chairs | Partner
Week 9 |  | October 26 - October 30
Week 10 |  | November 2 - November 6
Timeline for Spring 2027 posted |  |  | GA | REG
Last day to Withdraw with "W" on transcript, no refund (Friday) |  | 2026-11-06 |  |  | Students
Week 11 |  | November 9 - Noveember 13
Teaching Schedule for Spring 2027 |  |  | Partner |  | GA
Application of Completion (Intent to Graduate) list sent to Registrar office for students expecting to graduate in Spring 2027 |  |  | Partner | REG
Partners send official transcripts to FHSU Registrar for students to be admitted for Spring 2027 semester |  |  | Partner | REG
Week 12 |  | November 16 - November 20
Teaching Assignments for Spring 2027 - Final |  |  | Chairs | GA | Partner
Partner Transcripts: 6th semester IP Transcript sent to Registrar's office |  | TBD | Partner | REG
Week 13 |  | November 23 - November 27
Partner Transcripts: Final additions or changes for Fall 2026 graduates |  |  | Partner | REG
Week 14 |  | November 30 - December 4
Student Evaluations Open (two weeks before finals) |  |  | TS
Week 15 |  | December 7 - December 11
Week 16 |  | December 14 - December 18
Last week of Classes
Student Evaluations of courses close |  |  | TS |  | Students
Post Term
FHSU faculty submit final grades to FHSU Registrar |  | 2027-01-04 | Faculty | REG | Faculty, GA
Partner Transcripts: 7th Semester Transcripts for Spring 2027 graduates |  | 2027-01-08 | Partner | REG
Report ran to determine missing final grades |  |  | GA |  | Chairs
Fall 2026 grade report available in Workday |  |  | FHSU | REG | GA
Grades available on the IP Portal |  |  |  |  | Students
Academic Standing Report |  |  | GA |  | Partner/REG
Diplomas and transcripts of students graduating Fall 2026 shipped to partners |  | 2027-02-08 | REG |  | GA/Partners
ASC - CbyD Grades sent to FHSU Registrar Office |  | 2027-01-06 | Partner | REG | GA
Pre-Spring Term
Teaching Assignments entered and cross-checked in Workday for Spring 2027 |  |  | Chairs | Registrar | BB
Blackboard shells open to faculty for Spring 2027 (4 weeks prior to Spring term) |  |  | TS |  | Faculty
Admission and Transcript reports: Late Admits |  | Feb 10 - 14??? | Partner | Admissions/REG | Admissions/REG
Deadline for chairs to have FHSU Online Course Requests submitted to the Registrar - New Process |  | 2027-01-19 | GA | Chairs | Partner
Spring27 Term
TENTATIVE Start Dates |  | 2027
FHSU University Breaks and Holidays
2026-09-07 |  | Labor Day
11/23/2026 - 11/27/2026 |  | Thanks giving Break
12/25/2026- 1/3/2027 |  | Winter Break - University Closed
Chinese Holidays
September-17-2025 |  | Mid-Autumn Festival
October 1-7-2025 |  | National Holiday
January-1-2027 |  | New Year's Day
Notes:
Workday to Blackboard Integration runs three times daily (5p, 6p, 7p Central Time)
Global Blackboard: https://globalbb.fhsu.edu/
Academic and Operational Team
Academic Administration | Jeni McRay (at FHSU)
Academic Standing | Beth Spencer
Faculty | FHSU International Faculty
HR - Human Resources | Russel Irby
Kenadee O'brien
RCOBE Director of Strategic Partnerships | Robert Lloyd
Department Chair/Administrative Assistant | Paul Nienkamp/Jodie Wear-Leiker (PHIL)
Department Chair/Administrative Assistant | Steve Sedbrook/Noel Sanderson (HHP)
Anthony Fox (HHP)
Department Chair/Administrative Assistant | Eric Leuschner/Amy Richecky (ENG)
Cross Border Education Specialist | Sharon Graham (UNIV)
TS - Technology Services | Greg Grammon - Server
Michael Leibold - Blackboard
GAISS - Global Affairs International Services | Haley Williams
Phil Wittkorn
Jadyn Snyder (faculty HR processes/visa/travel)
Cassie Smith (admissions)
Zoey Sneed
Registrar - Registrar's Office | Craig Karlin (Registrar)
Becky Newel (Assistant Registrar)
Sheila McGuire (Course Scheduling)
Nikki Houchen (Degree Analyst/Student Records)
Tammy Winters (Grades/Course Registrations)
SFS - Student Fiscal Services | Dane Lonnon
Lincoln Hector
Institutional Research and Eff. | Darren Stieben
TLC - The Language Company | Brenda Robati
Partner - SNU - Academics | Steven (Yuzhou Cai)
Yolanda (Jing Yang)
Daisy (Qi Dongyan)